## Problem 1
Chapter 16, Problem 1
Job | Customer Pick-Up Time | Remaining Time | Remaining Operation | Slack Time
A | 10 | 4 | Painting | 4
B | 27 | 5 | Wheel Alignment, Painting | 5
C | 15 | 1 | Chrome Plating, Painting, Seats | 1
STR | Processing Time | Due | Flow Time | Slack Time
C | 14 | 15 | 0+14=14 | 1
A | 6 | 10 | 14+6=20 | 4
B | 12 | 17 | 20+12=32 | 5

## Problem 3
Chapter 16, Problem 3
| M | T | W | R | F | S | S
Requirements | 2 | 2 | 1 | 3 | 3 | 4 | 2
W1 | 2 | 2 | 1 | 3 | 3 | 4 | 2
W2 | 1 | 2 | 1 | 2 | 2 | 3 | 1
W3 | 1 | 1 | 0 | 1 | 1 | 2 | 1
W4 | 0 | 0 | 0 | 1 | 0 | 1 | 0

## Problem 5
Chapter 16, Problem 5
Job | Required Time | Days to Delivery | Slack
A | 8 | 12 | 4
B | 3 | 9 | 6
C | 7 | 8 | 1
D | 1 | 11 | 10
E | 10 | -10 | -20
F | 6 | 10 | 4
G | 5 | -8 | -13
H | 4 | 6 | 2
A) SOT
Job | Time | Days | Slack | Flow Time
D | 1 | 11 | 10 | 1+0=1
B | 3 | 9 | 6 | 1+3=4
H | 4 | 6 | 2 | 4+4=8
G | 5 | -8 | -13 | 8+5=13
F | 6 | 10 | 4 | 13+6=19
C | 7 | 8 | 1 | 19+1=20
A | 8 | 12 | 4 | 26+8=34
E | 10 | -10 | -20 | 34+10=44
|  |  | Average Flow Time: | 5.5
B) Activities E & G First
Job | Time | Days | Slack | Flow Time
E | 10 | -10 | -20 | 10+0=10
G | 5 | -8 | -13 | 10+5=15
D | 1 | 11 | 10 | 15+1=16
B | 3 | 9 | 6 | 16+3=19
H | 4 | 6 | 2 | 19+4=23
F | 6 | 10 | 4 | 23+6=29
C | 7 | 8 | 1 | 29+7=36
A | 8 | 12 | 4 | 36+8=44
|  |  | Average Flow Time: | 5.5

## Problem 7
Chapter 16, Problem 7
Job | Days of Actual Processing Time Required | Days of Necessary Delay Time | Total Time Required | Date Job Due | Critical Ration 1
1 | 2 | 12 | 14 | 30 | 1.8
2 | 5 | 8 | 13 | 21 | 1.2
3 | 9 | 15 | 24 | 28 | 1.6667
4 | 7 | 9 | 16 | 29 | 1.7333
5 | 4 | 22 | 26 | 27 | 1.6
CR Method
Job | Total Time Required | Critical Ration
2 | 13 | 1.2
5 | 26 | 1.6
3 | 24 | 1.67
4 | 16 | 1.73
1 | 14 | 1.8
SOT Method
Job | Total Time Required | Flow Time
2 | 13 | 13+0=13
1 | 14 | 14+13=27
4 | 16 | 27+16=43
3 | 24 | 24+43=67
5 | 26 | 67+26=93

## Problem 12
Chapter 16, Problem 12
Car | Customizing Time (Hours) | Painting (Hours) | Order of Selection | Position In Sequence
1 | 3 | 1.2 | 4 | 8
2 | 2 | 0.9 | 6 | 7
3 | 2.5 | 1.3 | 3 | 9
4 | 0.7 | 0.5 | 10 | 4
5 | 1.6 | 1.7 | 1 | 1
6 | 2.1 | 0.8 | 7 | 6
7 | 3.2 | 1.4 | 2 | 10
8 | 0.6 | 1.8 | 8 | 3
9 | 1.1 | 1.5 | 5 | 2
10 | 1.8 | 0.7 | 9 | 5

## Problem 13
Chapter 16, Problem 13
Job | Processing Time (Days) | Due Date | Slack Time
A | 4 | 20 | 16
B | 12 | 30 | 18
C | 2 | 15 | 13
D | 11 | 16 | 5
E | 10 | 18 | 8
F | 3 | 5 | 2
G | 6 | 9 | 3
A) What is the FCFS schedule? |  |  |  | C) What is the STR schedule?
Job Sequence | Processing Time (Days) | Due Date (Days Hence) | Flow Time (Days) | Job Sequence | Processing Time (Days) | Due Date (Days Hence) | Flow Time (Days)
A | 4 | 20 | 4 | F | 3 | 5 | 3
B | 12 | 30 | 16 | G | 6 | 9 | 9
C | 2 | 15 | 18 | D | 11 | 16 | 20
D | 11 | 16 | 29 | E | 10 | 18 | 30
E | 10 | 18 | 39 | C | 2 | 15 | 32
F | 3 | 5 | 42 | A | 4 | 20 | 36
G | 6 | 9 | 48 | B | 12 | 30 | 48
|  | Total Flow Time: | 196 |  |  | Total Flow Time: | 178
|  | Average Flow Time: | 28 |  |  | Average Flow Time: | 25.4286
B) What is the SOT schedule? |  |  |  | D) What is the Ddate schedule?
Job Sequence | Processing Time (Days) | Due Date (Days Hence) | Flow Time (Days) | Job Sequence | Processing Time (Days) | Due Date (Days Hence) | Flow Time (Days)
C | 2 | 15 | 2 | F | 3 | 5 | 3
F | 3 | 5 | 5 | G | 6 | 9 | 9
A | 4 | 20 | 9 | C | 2 | 15 | 11
G | 6 | 9 | 15 | D | 11 | 16 | 22
E | 10 | 18 | 25 | E | 10 | 18 | 32
D | 11 | 16 | 36 | A | 4 | 20 | 36
B | 12 | 30 | 48 | B | 12 | 30 | 48
|  | Total Flow Time: | 140 |  |  | Total Flow Time: | 161
|  | Average Flow Time: | 20 |  |  | Average Flow Time: | 23

## Problem 14
Chapter 16, Problem 14
Job | Machine 1 | Machine 2 | Order of Selection | Position In Sequence
1 | 5 | 2 | 2 | 6
2 | 16 | 15 | 6 | 2
3 | 1 | 9 | 1 | 1
4 | 13 | 11 | 5 | 3
5 | 17 | 3 | 3 | 5
6 | 18 | 7 | 4 | 4
Total Flow Time: |  | 48